## Sheet1
# | Sprint | Module | Module Desc | PIC | Priority | StartDate | DueDate | Status
0 | 1 | Candidate | UC05 View Candidate List UC06: Create new Candidate UC08: Edit Candidate Information UC09: Delete Candidate |  |  |  | 14h 30/12/2024 | PENDING
|  | Offer | UC23: View offer list UC24 Create new offer UC25 Edit offer |  |  |  | 14h 30/12/2025 | PENDING
|  | Interview | UC16 View interview schedule UC17 Create interview schedule UC20 Edit interview |  |  |  | 14h 30/12/2026 | PENDING
1 | 2 | Job | UC12 Create Job UC11 View job list UC14 Edit job UC15 Delete job |  |  |  | 14h 30/12/2028 | PENDING
|  | Auth + User | UC32 View user list UC33 Create new user UC35 Edit user |  |  |  | 14h 30/12/2029 | PENDING

## Sheet2
# | Sprint | Tasks | Module | Module Desc | PIC | Priority | StartDate | DueDate | Status
0 | 1 | Design Database | x | x |  |  | 2025-12-03 | 14/3/2025 | Done
|  | Design UI on Figma | x | x |  |  | 14/3/2025 | 15/3/2025 | On Progress
|  | Skeleton for BE | x | x |  |  | 16/3/2025 | 18/3/2025 | Not Started
|  | Skeleton for FE | x | x |  |  | 16/3/2025 | 18/3/2025 | Not Started
|  | HTML Code for UI | x | x |  |  | 16 -17/3/2025 | 18/3/2025 | Not Started
1 | 2 | Develop Basic User Management & Ticket Booking Functionality | Authentication | Develop API for account registration and login. Create unit test for module Authentication. |  |  |  |  | Not Started
Not Started
|  |  | UserManagement | Build models, controllers, and services for user authentication handling. Create unit tests for the authentication module. |  |  |  |  | Not Started
Not Started
|  |  | Inital Ticket Booking | Design initial APIs to retrieve the list of movies and showtimes. |  |  |  |  | Not Started
2 | 3 | Implement Ticket Booking & Ticket Selling – Employee Management | Authentication | Develop API for account registration and login. Create unit test for module Authentication. |  |  |  |  | Done
Not Started
|  |  | UserManagement | Build models, controllers, and services for user authentication handling. Create unit tests for the authentication module. |  |  |  |  | Not Started
Not Started
|  |  | Inital Ticket Booking | Design initial APIs to retrieve the list of movies and showtimes. |  |  |  |  | Not Started
3 | 4 |  | Authentication | Develop API for account registration and login. Create unit test for module Authentication. |  |  |  |  | Not Started
Not Started
|  |  | UserManagement | Build models, controllers, and services for user authentication handling. Create unit tests for the authentication module. |  |  |  |  | Not Started
Not Started
|  |  | Inital Ticket Booking | Design initial APIs to retrieve the list of movies and showtimes. |  |  |  |  | Not Started